SCOPE OF WORK

A.	Purpose:  The Contractor shall develop a Business Continuity Plan (BCP) for the California Health Benefit Exchange (Exchange). The Contractor will be required to conduct a Business Impact Analysis (BIA), create recovery strategies, and develop, assemble, validate, and submit a final BCP. The Exchange has three main worksites, two of which are Service Centers (call centers).

B.	Background Clearance: If the Contractor must access any confidential information, this provision must be completed prior to implementing any portion of this scope of work.

Prior to accessing any confidential information, personal identifying information, personal health information, federal tax information, or financial information contained in the information systems and devices of the Exchange, or any other information as required by federal and State law or guidance, all staff, including employees, contract or subcontract personnel, vendors or volunteers who perform services under this Agreement must comply with the criminal background check requirements set forth in Government Code section 1043, and its implementing regulations set forth in California Code of Regulations, Title 10, section 6456.

C.	General Scope or Tasks:

- Scope and Description:

  - Business Impact Analysis (BIA):

    - The Contractor shall develop a questionnaire to release to the various Divisions in the agency.

    - The Contractor shall conduct a workshop to instruct liaisons from the Divisions on how to complete the BIA questionnaire.

    - The Contractor shall review the responses, in collaboration with the agency, and conduct follow up interviews to validate information to fill any information gaps.

    - The Contractor shall draft the BIA and submit to the agency for leadership review and approval. The Contractor will make any recommended changes to the draft BIA as requested by the agency and finalize the document.

    - This task should not take more than 100 days to complete.

  - Recovery Strategies:

    - The Contractor shall work with the agency to identify and document resource requirements based on the information gathered in the BIA.

    - The Contractor shall conduct a gap analysis to determine gaps between the recovery requirements and the current capabilities.

    - The Contractor shall prepare a final report to recommend and document recovery strategy options and present to the agency for leadership approval. The Contractor will make any recommended changes to the draft recovery strategy options as requested by the agency and finalize the document.

    - This task should not take more than 100 days to complete.

  - BCP Development:

    - The Contractor shall develop a BCP framework.

    - The Contractor shall work with the agency to organize recovery teams.

    - The Contractor shall develop relocation plans.

    - The Contractor shall document manual workarounds.

    - Using this information, the Contractor shall assemble the BCP, validate the document, and submit to the agency for leadership approval. The Contractor will make any recommended changes to the draft BCP as requested by the agency and finalize the document.

    - This task should not take more than 45 days to complete.

  - Testing and Exercises:

    - The Contractor shall develop testing, exercise and maintenance requirements, and provide a final report to the agency.

    - This task should not take more than 45 days to complete.

- Deliverables: Deliverables include:

- BIA Draft and Final Report;

- Recovery Strategies Draft and Final Report;

- BCP Draft and Final Plan; and

- Testing and Exercises.

- Other Reporting Requirements: On a (weekly or monthly) basis, each contractor staff person shall complete a timesheet.

- Travel: Travel is not reimbursed under this agreement.

D.	Reporting Headquarters Location:

The Contractor is required to perform all services under this Agreement on site at the Exchange, unless directed otherwise by the project representative listed in this Exhibit.  The Exchange office is located at 1601 Exposition Boulevard, Sacramento, California, 95815.  Travel and expenses for reporting to this headquarters location shall not be reimbursed.

E.	Contract Deliverables:

- The Contractor understands that all recommendations and contract deliverables must comply with the Patient Protection and Affordable Care Act of 2010, as well as sections 15438, 15439, and 100501 through 100521 of the Government Code; 1346.2 and 1366.6 of the Health and Safety Code; 10112.3 and 10112.4 of the Insurance Code.

- The Contractor shall provide all deliverables within the timeframe specified and required by the State.

- The Contractor understands and acknowledges that all deliverables must be reviewed, approved and accepted by the State.

- The Contractor understands that any State-requested revisions to any deliverable shall be incorporated by the Contractor within seven calendar days from the date in which the State provided its feedback, unless a different timeframe is required and specified by the State.

- In the event the State requires additional refinements and modifications for any deliverable which occurs after that deliverable has been previously accepted by the State, the Contractor shall be required to make the additional revisions until the revised deliverable is accepted and approved by the State.

- The Contractor shall be paid for services rendered under this Agreement in accordance with Exhibit B, Budget Detail and Payment Provisions.

F.	Roles and Responsibilities:

The Contractor shall:

- Designate a person to whom all project communications may be addressed and who has the authority to act on all aspects of the contract for services. This person will be responsible for the overall project and will be the contact for all invoice and Contractor staffing issues.

- Provide written reports for review and approval by Covered California and formally respond to Covered California review findings as necessary.

- Meet weekly with Covered California staff to discuss progress.

- Make its best efforts to maintain staff continuity throughout the life of the project. If, however, a substitution becomes necessary, the Contractor must submit a resume for review, in advance, of all proposed personnel substitutions. All Contractor personnel substitutions must be approved in writing by Covered California’s Project Manager. Failure to receive the required approvals may result in termination of the contract.

The Exchange shall:

- Designate Covered California contact person (Project Manager) to whom all Contractor communications may be addressed and who has the authority to act on all aspects of the services. This person will review the contract and associated documents with the Contractor to ensure understanding of the responsibilities of both parties.

- Provide access to business and technical documents as necessary for the Contractor to complete the tasks identified in this RFP.

- Ensure appropriate resources are available to perform assigned tasks, attend meetings, and answer questions.

- Ensure that decisions are made in a timely manner.

- Provide work areas and meeting rooms as needed.

- Identify and provide access to Subject Matter Experts to assist with the elaboration of technical requirements.

G.	Project Representatives:

The representatives for this project, during the term of this Agreement, shall be:

| State Program Representative | Contractor Representative: |
| --- | --- |
| (Representative’s Name) California Health Benefit Exchange 1601 Exposition Blvd. Sacramento, CA 95815 (916) XXX-XXXX T (916) XXX-XXXX F (Email Address) | (Contractor’s Name) (Representative’s Name) (Address) (City, State and Zip) (Telephone Number) (Fax Number) (Email Address) |