SCOPE OF WORK (SOW)

- Purpose:

The purpose of this Agreement is to provide the California Health Benefit Exchange (hereafter referred as “Covered California” or the “Exchange”) with qualified academic or research organizations to undertake quantitative research services. The need for consumer research and evaluation is particularly important as Covered California continues to improve efforts to target consumers, manage customer satisfaction, increase loyalty and promote services to meet acquisition, retention and renewal goals.

Contractor will perform the following core tasks when executing the SOW

- Support Covered California’s mission, goals, objectives and priorities primarily through quantitative research to improve the understanding of its membership, the consumer experience and role in the California health insurance marketplace.

- Develop and implement a comprehensive approach to quantitative research efforts including statewide tracking studies, consumer surveys and research planning.

- Provide a core team, including a Project Lead responsible for all areas of the SOW, capable of directing simultaneous projects to completion.

- Provide daily oversight and strategic guidance of any necessary personnel, subcontractors, consultants and vendors utilized to successfully achieve the deliverables detailed in this SOW.

- Background Clearance:

If the Contractor must access any confidential information, this provision must be completed prior to implementing any portion of this scope of work.

Prior to accessing any confidential information, personally identifiable information, personal health information, federal tax information, or financial information contained in the information systems and devices of Covered California, or any other information as required by federal and State law or guidance, all staff, including employees, contract or subcontract personnel, vendors or volunteers who perform services under this Agreement must comply with the criminal background check requirements set forth in Government Code section 1043, and its implementing regulations set forth in California Code of Regulations, Title 10, section 6456. Contractor shall bear all costs associated with obtaining clearance for each said employee.

- Requirements Common to All Project Areas: 

In addition to the requirements stated in each Project Area (Sections D-G below), the Contractor shall perform the following when executing the Scope of Work:

  - Evaluate existing Covered California instruments, methodologies, and plans, and collaborate in revising or creating new approaches as necessary.

  - Establish comprehensive methodologies for data sampling, collection and analysis for each research project.

  - Prepare and deliver a project plan and estimate for each survey, including sufficient advanced timeframes to meet necessary delivery goals.

  - Produce survey instruments in both English and Spanish, including translation services of responses or other material as required.

  - Develop, pre-test, produce, and deliver survey instruments to consumers in the agreed-upon mode(s) (online, phone, etc.).

  - Field surveys at the appropriate time (i.e. post-renewal and open enrollment periods, or following a specific consumer action).

  - Allow for adding or deleting questions between survey waves.

  - Collect, clean, and process data for analysis, including post-stratification weights, statistical frequencies and analysis by select variables (e.g. region, race, ethnicity, language, etc.)

  - Produce analytic files, basic code books, and functional narratives for how to use the weights and other key variables.

  - Provide copies of scientific studies, research, and calculations used to substantiate data, if necessary.

  - Produce comprehensive topline and full reports according to industry standards at the conclusion of each survey for showing raw and weighted counts for each item on the surveys.

  - Report on “Lessons Learned” and strategic recommendations to support improvements on future surveys.

- Project Area 1 – Consumer Tracking Study of Brand Awareness, Attitudes and Knowledge:

Contractor shall perform the following tasks as they relate to Project Area 1:

  - Measure consumer awareness (aided and unaided) of the Covered California brand through metrics of recognition, recall and favorability.

  - Measure consumer attitudes toward Covered California and the impact of these attitudes on consumer behavior with regard to enrolling or maintaining health insurance through Covered California.

  - Measure consumer knowledge (aided and unaided) including but not limited to:

      - Covered California and its services, benefits and offerings;

      - Process and methods of enrolling through Covered California;

      - Aspects of the Affordable Care Act or new legislation (tax credit, penalty, comparability of plans, etc.); and,

      - Aspects of health insurance (enrollment periods, copays, deductibles, etc.).

- Project Area 2 – Consumer Tracking Study of Advertising Effectiveness: 

Contractor shall perform the following tasks as they relate to Project Area 2:

- Measure consumer awareness (aided and unaided), knowledge and recall of Covered California’s:

  - Key advertising topics (value of health insurance, financial help, services, deadlines, etc.).

  - Creative executions (TV, radio, digital, etc.).

  - Specific messaging.

- Measure the impact of the marketing efforts on consumer behavior to consider, enroll or maintain health insurance through Covered California.

3.	Compare consumer behavior in terms of purchase intent and other factors between those who have differing levels of awareness, knowledge, impact and recall of Covered California’s advertising.

F.  Project Area 3 – Covered California Member Survey: 

Contractor shall perform the following tasks as they relate to Project Area 3:

- Produce survey plans and make recommendations on survey implementation to ensure an optimal response rate.

- Provide survey sampling and data collection plans utilizing phone, paper, or email survey modalities to optimize the representativeness of the survey.

- Provide survey analysis plans, including comparison of respondents and non-respondents, by survey mode, on key variables; recommended subgroup analyses to meet learning objectives.

- Implement ongoing, timely member surveys.

- Project Area 4 – Technical Assistance: Project Management, Research Planning, Additional Surveys and Other Services: 

Contractor shall perform the following tasks as they relate to Project Area 4:

      - Provide project management services to all project areas of the SOW.

      - Provide consultation to improve and maximize Covered California’s quantitative research efforts, and the strategic planning, development, and implementation of its evaluation activities.

      - Assist in evaluating and revising existing surveys in the context of other proposed research, and develop and implement new surveys to evaluate aspects of the consumer experience (i.e. satisfaction measures).

      - At Covered California’s discretion, provide as-needed services in support of research efforts that are within the contract’s SOW but are not explicitly addressed. These services may include, but are not limited to:

    - Qualitative research (e.g. focus groups);

    - Different modalities of data collection (e.g. intercepts, text);

    - Ad-hoc requests for research and/or data; and,

    - Consultation on research projects.

- Specialized Programs:

Upon Covered California’s request, Contractor shall perform the following specialized programs:

  - Provide as-needed services that are within the contract’s SOW but are not specifically addressed in this RFP.

    - Compensation for Specialized Program services will be based on the agreed-upon billing rate listed in Exhibit B, Attachment 1, Cost Worksheet.

    - All Specialized Program services will require submission of a work plan prior to the start of any work and must be approved in writing by a Covered California Representative or designee.

- Location of Contractor Staff:

  - The Contractor shall assign a Project Lead, responsible for managing day-to-day operations. The Project Lead must be available to be at Covered California headquarters within 24 hours of receiving a request to appear from Covered California. Covered California’s request may be verbal, written, or electronic. Contractor will immediately notify Covered California if it is unable to comply with the request.

- Subcontractors

  - The Contractor shall, if it does not have the full-service capabilities to effectively address all project areas of the SOW, obtain subcontractors to perform the necessary tasks that it cannot perform itself.

  - Covered California reserves the right to deny any or all proposed subcontractors selected by the Contractor.

- Work Orders:

The Contractor shall perform all services under this Agreement according to the work order procedures in this section.

  - Work orders are the detailed descriptions of services and deliverables to be provided pursuant to this Agreement, which must include a comprehensive plan, budget, and timeline for providing each service or deliverable. Billings will be tracked on a project basis and will require the submission and approval of a work order for all elements in this SOW that will result in billable costs. Work orders for ongoing activities will be due within thirty (30) calendar days of the start of this Agreement and on June 1 of each state fiscal year (July 1 through June 30) thereafter. Work orders for intermittent activities or special projects will be developed and submitted as requested by the Covered California Representative listed in this Exhibit, and must be signed by the Covered California Representative. Any work performed by the Contractor or its subcontractors, consultants or vendors that is not covered by an approved work order is undertaken at the Contractor's own risk.

  - The Contractor is responsible for submitting work orders for all work performed under this Agreement, including any services and deliverables performed or provided in whole or in part by subcontractors, consultants or vendors. Subcontractors, consultants and vendors shall not submit work orders directly to Covered California. Work orders for work to be completed by subcontractors, consultants and vendors shall be signed and submitted by Contractor for review by Covered California.

  - The work order must include, at a minimum, the following information:

- Agreement number, Contractor's name, date submitted and a unique work order name and number assigned by the Contractor;

- A description of the populations to be addressed/surveyed and the strategy and objective of the services and deliverables to be provided by the Contractor under the work order;

- A detailed description of the services and deliverables to be provided during completion of the work order, including identification of any service(s) or deliverable(s) to be provided by a subcontractor or consultant;

- The time period covered by the work order and a detailed timeline for completion of the service or deliverable;

- Contractor Representative's printed or typed name and signature and date signed; and,

- Spaces for the Covered California Representative’s printed or typed name and signature and date signed.

  - The Covered California Representative shall review the Contractor’s proposed work order and may require the Contractor to revise portions or all the proposed work order to the satisfaction of the Covered California Representative.

  - The Covered California Representative’s signature approval of the work order shall constitute the Contractor’s authorization to provide the work order’s service or deliverable under this Agreement. Approved work orders shall become a part of this agreement without the need for a formal amendment, and, as such, the terms and conditions of this Agreement shall apply to the services performed under these work orders. Any approved work orders may be changed by mutual agreement of the parties without a formal amendment to this Agreement.

  - The Covered California Representative may terminate a work order in whole or in part for any reason and at any time, including after it has been approved by providing two (2) days prior written notice to Contractor. Termination shall occur if Covered California no longer desires the service(s) or deliverable(s), due to program changes or lack of funding, or other circumstances. The Covered California Representative shall notify the Contractor in writing whenever a work order is terminated and shall negotiate in good faith with the Contractor to determine the payment for any deliverables completed or in process and services provided under the work order prior to termination. The notice of termination shall include the effective date of termination of the work order.

  - The Contractor shall track and report approved budgets as specified on work orders and actual spend amounts on invoices on a monthly basis, which are reconciled by the close of each state fiscal year (June 30).

  - Any additional work conducted by Contractor using Covered California data or their derivatives is considered owned by Covered California and must be reviewed and approved prior to release.

- Progress Reports and Meetings:

The Contractor shall:

- Develop a management and monitoring plan for keeping Covered California apprised of all contract activities, current personnel and subcontractors or vendors responsible for activities, and an evaluation of the effectiveness and cost efficiency of these activities.

- At intervals determined by Covered California, provide updates of open projects, work orders and timelines, and provide communication of interim findings and special problems encountered so that remedies can be developed quickly.

- Hold ongoing meetings at which Contractor shall present findings, conclusions, and comprehensive final reports of efforts and recommendations on how learnings could be applied moving forward.

10.	Key Personnel:

- The personnel specifically identified in Exhibit C, Attachment 1 (Resumes) are considered essential to the work under this Agreement.

- Key personnel may include subcontractors. The Contractor is responsible for all performance under this Agreement completed by a subcontractor.

- Before removing, replacing or diverting any of the listed or specified personnel, the Contractor must notify the Covered California Representative in writing, in a timely manner, and submit justification (including proposed substitutions) in sufficient detail to permit evaluation of the impact on this Agreement.

- Covered California shall have final approval of essential staff listed in Exhibit C, Attachment 1 (Resumes).

- Notwithstanding the foregoing, Covered California understands and agrees that if such specified personnel ceases to be employed by Contractor for any reason, their unavailability shall not be deemed a breach of this Agreement.

- Samples:

Samples of items, work, goods, materials, products, deliverables, services and similar products and efforts may be required by Covered California for inspection and must be furnished to Covered California free of expense.

- Release of Work Products:

  - The Contractor shall not release or disclose any work products created, produced or developed pursuant to this contract to any person or entity, except to Contractor personnel, subcontractors and vendors. Work products include, but are not limited to drafts or works in progress.

  - The Contractor shall employ reasonable measures to protect these work products from unauthorized use and disclosure. Covered California retains the right to approve any procedures employed by the Contractor to comply with this provision.

- Contract Deliverable Provisions:

- The Contractor understands that all recommendations and contract deliverables must comply with the Patient Protection and Affordable Care Act of 2010, as well as sections 15438, 15439, and 100501 through 100521 of the Government Code; 1346.2 and 1366.6 of the Health and Safety Code; 10112.3 and 10112.4 of the Insurance Code.

- The Contractor shall provide all deliverables within the timeframe specified and required by Covered California.

- The Contractor understands and acknowledges that all deliverables must be reviewed, approved and accepted by Covered California.

- Contractor shall provide all deliverables in a timely fashion throughout the term of the contract once efforts are finalized and approved by Covered California. Contract closeout work product must be provided no later than 90 days after the expiration of the contract.

- The Contractor understands that any requested revisions by Covered California to any deliverable shall be incorporated by the Contractor within seven (7) calendar days from the date in which Covered California provided its feedback, unless a different timeframe is required and specified by Covered California, or as otherwise agreed to by the parties.

- In the event Covered California requires additional refinements and modifications for any deliverable which occurs after that deliverable has been previously accepted by Covered California, the Contractor shall be required to make the additional revisions until the revised deliverable is accepted and approved by Covered California.

- The Contractor shall be paid for services rendered under this Agreement in accordance with Exhibit B – Budget Detail and Payment Provisions.

- Contract Execution and Performance:

Work shall be performed by Contractor on an as-needed basis and as requested by Covered California.

- Contract Amendment:

Covered California may, at its sole discretion, extend the contract for two (2), one (1) year extensions, under the same terms and conditions, including pricing terms as set forth in Exhibit B.

- Project Representatives:

The representatives for this project, during the term of this Agreement, shall be:

| California Health Benefit Covered California Representatives: | Contractor Representative: |
| --- | --- |
| (Representative’s Name) Covered California 1601 Exposition Blvd. Sacramento, CA 95815 (916) XXX-XXXX T (Email Address) | (Representative’s Name) (Contractor’s Name) (Address) (City, State and Zip) (916) XXX-XXXX T (Email Address) |
| (Representative’s Name) Covered California 1601 Exposition Blvd. Sacramento, CA 95815 (916) XXX-XXXX T (Email Address) |  |